# Project Planning Phase: Product Backlog, Sprint Planning & Tracking

| Attribute | Details |
| --- | --- |
| Date | 30 September 2026 |
| Team ID | SWTID-2026-2901 |
| Project Name | LearnMate – AI Study Buddy API |
| Maximum Marks | 5 Marks |

## 1. Product Backlog, Sprint Schedule & Estimation

This backlog breaks down the LearnMate – AI Study Buddy API implementation into four prioritized delivery sprints using Fibonacci story point estimation (). Tasks are assigned across the development team based on specialization.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Engineering Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | User Authentication | USN-01 | As a student, I want to register an account with name, email, password, and role so my study resources remain private. | 2 | High | Srinivasan J |
| Sprint-1 | User Authentication | USN-02 | As a backend service, I must encrypt student passwords using bcryptjs with salt rounds = 10 before saving to MongoDB. | 2 | High | Srinivasan J |
| Sprint-1 | User Authentication | USN-03 | As an authenticated user, I can log in with valid credentials and receive dual JWT tokens (Access & Refresh tokens). | 3 | High | Srinivasan J, Vishal A M |
| Sprint-1 | Access Control & Security | USN-04 | As an API gateway, I need JWT verification middleware (auth.js) to reject unauthorized requests with HTTP 401 Unauthorized. | 2 | High | Vishal A M |
| Sprint-1 | Database Architecture | USN-05 | As a data architect, I need Mongoose schemas for User and Material with foreign key relationships and schema validation. | 3 | High | Atshaya R |
| Sprint-1 | Ingestion & Storage | USN-06 | As a student, I can upload .txt lecture notes via multipart/form-data (multer) and receive a unique materialId. | 3 | High | Srinivasan J, Atshaya R |
| Sprint-1 | Environment & Setup | USN-07 | Initialize Express MVC project repository, setup environment configurations (.env), and verify Atlas DB connection. | 2 | High | All Members |
| Sprint-2 | AI Summarization | USN-08 | As a student, I can request a high-yield summary for an uploaded materialId to review core concepts quickly. | 3 | High | Ashwini V |
| Sprint-2 | AI Integration Gateway | USN-09 | Configure Google Gemini 1.5 Flash client (src/utils/gemini.js) with isolated API keys and rate-limit guardrails. | 3 | High | Ashwini V |
| Sprint-2 | AI Flashcards Engine | USN-10 | As a student, I want active-recall flashcard decks generated as parseable JSON arrays [{ question, answer }]. | 3 | High | Ashwini V, Atshaya R |
| Sprint-2 | Data Sanitization | USN-11 | Build a sanitization utility (cleanJsonMarkdown) to strip markdown code fences (```json) before executing JSON.parse(). | 2 | High | Vishal A M |
| Sprint-2 | Database Persistence | USN-12 | Model and persist Summary and Flashcard collections linked via relational references to userId and materialId. | 3 | Medium | Atshaya R |
| Sprint-2 | Integration Testing | USN-13 | Construct Postman assertion collection validating HTTP 200 OK responses and JSON schemas for summaries and cards. | 2 | High | Vishal A M |
| Sprint-3 | AI Quiz Generation | USN-14 | As a student, I can generate a 5-question 4-option practice quiz ([A, B, C, D]) with answer keys to test exam readiness. | 5 | High | Ashwini V, Srinivasan J |
| Sprint-3 | Dynamic Study Planner | USN-15 | As a student, I can submit { goal, days, hoursPerDay } to generate a customized day-by-day revision schedule. | 3 | High | Ashwini V |
| Sprint-3 | Database Persistence | USN-16 | Create Quiz and StudyPlan Mongoose collections and implement cascading delete triggers when parent materials are deleted. | 3 | Medium | Atshaya R |
| Sprint-3 | Defect Remediation | USN-17 | Resolve prompt variable cross-contamination where summary, quiz, and study-plan handlers returned identical flashcard bodies. | 3 | High | Srinivasan J, Ashwini V |
| Sprint-3 | Performance Optimization | USN-18 | Place compound database indexes on { userId: 1, materialId: 1 } to guarantee sub-millisecond query retrieval. | 2 | Medium | Atshaya R |
| Sprint-4 | Administrative Oversight | USN-19 | As an administrator, I can view system statistics, query total registered users, and audit platform usage via /api/admin/*. | 3 | Medium | Srinivasan J |
| Sprint-4 | RBAC Enforcement | USN-20 | Verify that regular student tokens attempting to access administrative endpoints are blocked with HTTP 403 Forbidden. | 2 | High | Vishal A M |
| Sprint-4 | Error Envelope Standards | USN-21 | Implement centralized Express error-handling middleware returning standardized JSON error payloads ({ success: false, error }). | 2 | Medium | Srinivasan J |
| Sprint-4 | End-to-End UAT Testing | USN-22 | Execute the comprehensive 10-case UAT test suite in Postman Desktop Agent and document test evidence and pass logs. | 3 | High | Vishal A M |
| Sprint-4 | Release Documentation | USN-23 | Finalize solution architecture diagrams, API interface specifications, and project audit reports for final sign-off. | 2 | High | All Members |

## 2. Project Tracker, Velocity & Burndown Chart

### A. Sprint Execution Tracker

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 17 | 6 Days | 01 Feb 2025 | 06 Feb 2025 | 17 | 06 Feb 2025 |
| Sprint-2 | 16 | 6 Days | 08 Feb 2025 | 13 Feb 2025 | 16 | 13 Feb 2025 |
| Sprint-3 | 16 | 6 Days | 15 Feb 2025 | 20 Feb 2025 | 16 | 20 Feb 2025 |
| Sprint-4 | 12 | 6 Days | 22 Feb 2025 | 27 Feb 2025 | 12 | 27 Feb 2025 |
| Total | 61 | 24 Days | 01 Feb 2025 | 27 Feb 2025 | 61 | 27 Feb 2025 |

### B. Team Velocity Calculations

Velocity measures the amount of work a development team delivers over a set sprint cycle.

#### 1. Average Velocity Per Sprint ()

#### 2. Average Velocity Per Iteration Unit (Daily Velocity, )

Using the standard daily rate formula where each sprint runs for a planned duration of 6 working days:

- Calculation for Sprint-1:

- Calculation for Sprint-2:

- Calculation for Sprint-3:

- Calculation for Sprint-4:

### C. Release Burndown Chart (Work Remaining vs. Time)

The burndown chart tracks cumulative story points remaining across the 4-sprint development lifecycle.

Points
Remaining
  65 ▲
  61 ┼───● [Start: 61 pts]
  60 │   │\
  55 │   │ \
  50 │   │  \
  45 │   │   \
  44 ┼───┼────● [End of Sprint-1: 44 pts remaining]
  40 │   │    │\
  35 │   │    │ \
  30 │   │    │  \
  28 ┼───┼────┼───● [End of Sprint-2: 28 pts remaining]
  25 │   │    │   │\
  20 │   │    │   │ \
  15 │   │    │   │  \
  12 ┼───┼────┼───┼───● [End of Sprint-3: 12 pts remaining]
  10 │   │    │   │   │\
   5 │   │    │   │   │ \
   0 ┼───┴────┴───┴───┴──● [End of Sprint-4: 0 pts remaining] ───►
      Sprint-0  Sprint-1  Sprint-2  Sprint-3  Sprint-4       Time
      (Kickoff) (06 Feb)  (13 Feb)  (20 Feb)  (27 Feb)

#### Sprint-by-Sprint Burndown Schedule

| Milestone / Checkpoint | Working Day | Planned Remaining Points | Actual Remaining Points | Status / Sprint Deliverable |
| --- | --- | --- | --- | --- |
| Day 0 (Kickoff) | Day 0 | 61 | 61 | Backlog groomed; repository & Atlas cluster initialized |
| Sprint-1 Close | Day 6 | 44 | 44 | Auth endpoints, JWT guards & Multer file uploads completed |
| Sprint-2 Close | Day 12 | 28 | 28 | Gemini API gateway, summary & JSON flashcards active |
| Sprint-3 Close | Day 18 | 12 | 12 | 4-option MCQs, study planner & defect bug fixes completed |
| Sprint-4 Close | Day 24 | 0 | 0 | RBAC verified, Postman UAT passed, production release RC-1 |

## 3. Sprint Retrospective & Velocity Insights

- Velocity Consistency: The team maintained an average delivery rate of  (). Story estimation accuracy stayed high due to clear separation between data modeling (Atshaya R), API logic (Srinivasan J), GenAI prompts (Ashwini V), and testing (Vishal A M).

- Impediments Resolved: During Sprint-2 and Sprint-3, runtime JSON markdown wrappers and prompt template collisions were detected during automated Postman testing and resolved within the sprint buffer without schedule slippage.

- Delivery Outcome: All 23 user stories across 61 total story points reached "Done" criteria prior to the final User Acceptance Testing (UAT) sign-off on 28 February 2025.